## Bird-view Schedule
Iteration |  | 1 | 2 |  | 3 |  | 4 |  | 5 |  | 6
Task | Worker | 4 |  |  |  | 5 |  |  |  | 6
|  | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8
|  | 6/4-12/4 | 13/4-19/4 | 20/4-26/4 | 27/4-3/5 | 4/5-10/5 | 11/5-17/5 | 18/5-24/5 | 25/5-31/5 | 1/6-7/6 | 8/6-14/6
|  | W15(4) | W16(5) | W17(6) | W18(7) | W19(8) | W20(9) | W21(10) | W22(11) | W23(12) | W24(13) |  | Planned | Responsibilites
Setting up development environment (git) | All | [10 empty] | Finished |  | User context sensing: EL | Content aggregation: EL | bar: W15(4)
Set up base application (basic GUI) | All | [10 empty] | In progress |  | Data retrieval: BB | UI and UX: SMK | bar: W15(4)
Setup retrieval of GPS position | SMK, EL | bar: W16(5)
Send notification based on location | SMK, EL | bar: W17(6)
Decide on data sources (maps, restaurants) and APIs | BB, KJW | bar: W16(5)
Set up system to retrieve data via data source APIs | BB, KJW | bar: W17(6) to W18(7)
Setup basic content generation | SMK, BB, EL | bar: W18(7) to W19(8)
Prepare for mid-term presentation | All | W20(9): 2020-11-05
Construct notification to send to user with content (MVP) | SMK | bar: W20(9) to W21(10)
Add functionality to save POIs | SMK, KJW | bar: W20(9) to W21(10)
Add TTS functionality | EL, BB | bar: W20(9) to W22(11)
Revision of content generation | EL | bar: W22(11)
Develop smarter recommendation/scoring system | BB | bar: W22(11)
Refining user interface | SMK | bar: W22(11)
Buffer time | All | bar: W23(12) to W24(13)
Prepare for final presentation | All | bar: W23(12) to W24(13)
Project due | All | W24(13): 2020-08-06

## Schedule
Iteration No | Task ID | DESCRIPTION | TYPE | PLANNED DATETIME START | PLANNED DATETIME END | HOURS SPENT PLANNED | ACTUAL DATETIME START | ACTUAL DATETIME END | HOURS SPENT ACTUAL | STATUS | Is Critical Path | Not planned | LOCATION | FINAL COMMIT ID | SMK | BB | EL | KJW | Est Days | Act Days | Planned Prog Hrs | Prog Hrs | Non-Prog Hrs | ItrStatus | ItrNot planned
1 | 1 | First proper project meeting: Discussing project ideas | Team meeting - planning, admin & updates | 2020-04-03 13:30 | 2020-04-03 14:30 | 1:00 | 2020-04-03 13:30 | 2020-04-03 15:00 | 1:30 | Completed | Yes | No | Home |  | Attended | Attended | Attended | Attended | 0.041667 | 0.0625 | 0 | 0 | 0.0625 | 1Completed | 1No
1 | 2 | Online meeting - deciding on a project idea, organizing proposal presentation | Team meeting - planning, admin & updates | 2020-04-03 21:30 | 2020-04-03 22:30 | 1:00 | 2020-04-03 21:00 | 2020-04-03 23:17 | 2:17 | Completed | Yes | No | Home |  | Attended | Attended | Attended | Attended | #REF! | 0.095139 | 0 | 0 | 0.095139 | 1Completed | 1No
1 | 3 | Online meeting - preparing proposal presentation | Team meeting - planning, admin & updates | 2020-04-04 10:30 | 2020-04-04 11:00 | 0:30 | 2020-04-04 10:20 | 2020-04-04 11:10 | 0:50 | Completed | Yes | No | Home |  | Attended | Attended | Attended | Attended
1 | 4 | Online meeting - preparing proposal presentation | Team meeting - planning, admin & updates | 2020-04-05 21:00 | 2020-04-05 22:00 | 1:00 | 2020-04-05 21:00 | 2020-04-06 00:05 | 3:05 | Completed | Yes | No | Home |  | Attended | Attended | Attended
1 | 5 | Online meeting - preparing proposal presentation | Team meeting - planning, admin & updates | 2020-04-06 13:00 | 2020-04-06 14:00 | 1:00 | 2020-04-06 13:00 | 2020-04-06 14:45 | 1:45 | Completed | Yes | No | Home |  | Attended | Attended | Attended
1 | 6 | Setting up development environment (git) | Programming - Features | 2020-04-06 09:00 | 2020-04-12 21:00 | 2:00 | 2020-04-10 15:00 | 2020-04-10 17:00 | 2:00 | Completed | Yes | No | Home |  | Attended | Attended | Attended | Attended
1 | 7 | Set up base application (basic GUI) | Programming - Features | 2020-04-06 09:00 | 2020-04-12 21:00 | 2:00 | 2020-04-10 17:45 | 2020-04-10 18:20 | 0:35 | Completed | Yes | No | Home | 47911130ba540c6f3d53d2d4c2ed15f909a485c2 | Leader
2 | 8 | Setup retrieval of GPS position | Programming - Features | 2020-04-13 09:00 | 2020-04-19 21:00 | 4:00 | 2020-04-07 10:30 | 2020-04-21 23:50 | 7:00 | Completed | Yes | No | Home | a2d07de8b6eb02c4b4636a69f95a785100d631f4 | Leader |  | Leader
2 | 9 | Send notification based on location | Programming - Features | 2020-04-20 09:00 | 2020-04-26 21:00 | 5:00 | 2020-04-17 15:00 | 2020-04-21 23:50 | 5:00 | Completed | Yes | No | Home | a2d07de8b6eb02c4b4636a69f95a785100d631f4 | Leader |  | Leader
2 | 10 | Setup internal geofencing API | Programming - Features | 2020-04-20 09:00 | 2020-04-26 21:00 | 5:00 | 2020-04-21 13:40 | 2020-04-28 12:15 | 7:20 | Completed | Yes | No | Home | 632b65c41c859be2ffe9c23cfb2acb9e8822c917 |  |  | Leader
2 | 11 | Create GeofenceTriggeredActivity | Programming - Features | 2020-04-20 09:00 | 2020-04-26 21:00 | 2:00 | 2020-04-29 10:40 | 2020-04-29 11:40 | 0:58 | Completed | Yes | No | Home | 632b65c41c859be2ffe9c23cfb2acb9e8822c917 |  |  | Leader
2 | 12 | Decide on data sources (maps, restaurants) and APIs | Programming - Features | 2020-04-13 09:00 | 2020-04-19 21:00 | 7:00 | 2020-04-13 09:00 | 2020-04-20 13:00 | 4:30 | Completed | Yes | No | Home | - | Attended | Leader | Attended | Attended
2 | 13 | Set up system to retrieve data via data source APIs | Programming - Features | 2020-04-13 09:00 | 2020-05-03 21:00 | 15:00 | 2020-04-13 09:00 | 2020-05-04 09:00 | 18:20 | Completed | Yes | No | Home | 202150e920b46683deb3a7157dc414a0d4f5cf12 | Attended | Leader |  | Attended
2 | 25 | Setup Wikipedia information retrieval | Programming - Features | 2020-04-28 09:00 | 2020-05-03 21:00 | 4:00 | 2020-05-01 13:45 | 2020-05-01 23:00 | 9:00 | Completed | Yes | No | Home | 70f169cc9cd82a0d17b22a8f4d28e3a4cbab9faf | Leader
2 | 26 | Online meeting - check up | Team meeting - planning, admin & updates | 2020-04-26 19:00 | 2020-04-26 20:00 | 1:00 | 2020-04-26 19:00 | 2020-04-26 20:00 | 1:00 | Completed | Yes | Yes | Home |  | Attended | Attended | Attended
3 | 14 | Setup basic content generation, combine info | Programming - Features | 2020-04-27 09:00 | 2020-05-10 21:00 | 5:00 | 2020-05-08 21:00 | 2020-05-08 19:00 | 3:00 | Completed | Yes | No | Home |  | Attended | Attended | Attended
3 | 15 | Prepare for mid-term presentation | Milestone - Presentations | 2020-04-27 09:00 | 2020-05-10 21:00 | 5:00 | 2020-05-08 21:00 | 2020-05-11 23:00 | 7:00 | Completed | Yes | No | Home |  | Attended | Attended | Attended
3 | 27 | Online meeting - mid term meeting | Team meeting - planning, admin & updates | 2020-05-08 12:30 | 2020-05-08 13:30 | 1:00 | 2020-05-08 12:50 | 2020-05-08 13:55 | 1:05 | Completed | Yes | Yes | Home |  | Attended | Attended | Attended
3 | 28 | Online meeting - meeting for mid-term | Team meeting - other | 2020-05-11 17:50 | 2020-05-11 19:00 | 1:10 | 2020-05-11 17:50 | 2020-05-11 19:00 | 1:10 | Completed | Yes | Yes | Home |  | Attended | Attended | Attended
3 | 29 | Online meeting - dry run meeting for mid-term | Milestone - Preparation | 2020-05-11 22:00 | 2020-05-11 22:40 | 0:40 | 2020-05-11 22:00 | 2020-05-11 22:40 | 0:40 | Completed | Yes | Yes | Home |  | Attended | Attended | Attended
4 | 16 | Construct notification to send to user with content (MVP) | Programming - Features | 2020-05-11 09:00 | 2020-05-24 21:00 | 10:00 | 2020-05-08 21:00 | 2020-05-08 21:00 | 5:00 | Completed | Yes | No | Home |  | Leader |  | Attended
4 | 17 | Add functionality to save POIs | Programming - Features | 2020-05-11 09:00 | 2020-05-24 21:00 | 10:00 |  |  |  | Not started | No | No | Home |  | Leader |  |  | Leader
4 | 18 | Add TTS functionality | Programming - Features | 2020-05-04 09:00 | 2020-05-24 21:00 | 15:00 |  |  |  | Not started | No | No | Home |  |  | Leader | Leader
5 | 19 | Revision of content generation | Programming - Features | 2020-05-25 09:00 | 2020-05-31 09:00 | 10:00 |  |  |  | Not started | No | No | Home
5 | 20 | Develop smarter recommendation/scoring system | Programming - Features | 2020-05-25 09:00 | 2020-05-31 09:00 | 10:00 |  |  |  | Not started | No | No | Home
5 | 21 | Refining user interface | Design - other | 2020-05-25 09:00 | 2020-05-31 09:00 | 10:00 |  |  |  | Not started | No | No | Home
5 | 23 | Prepare for final presentation | Milestone - Preparation | 2020-06-01 09:00 | 2020-06-08 23:59 | 10:00 |  |  |  | Not started | Yes | No | Home
6 | 22 | Buffer time | Other | 2020-06-01 09:00 | 2020-06-08 23:59 | 168:00 |  |  |  | Not started | No | No | Home
6 | 24 | Project due | Milestone - Presentations | 2020-06-08 23:59 | 2020-06-08 23:59 | 0:05 |  |  |  | Not started | Yes | No | Home

## Metrics
Burndown
Iteration No. | Planned | Actual
0 | 307:25 | 307:25
1 | 298:55 | 295:23
2 | 255:55 | 242:15
3 | 243:05 | 229:20
4 | 208:05 | 224:20
5 | 168:05 | 224:20
6 | 0:00 | 224:20
7 | 0:00 | 224:20
TM | §Actual tasks / Estimated tasks completed
Iteration No. | Planned Tasks | Completed Tasks | TM
1 | 7 | 2 | 0.28571
2 | 8 | 0 | 0
3 | 5 | 0 | 0
4 | 3 | 0 | 0
5 | 4 | 0 | 0
6 | 2 | 0 | 0
7 | 0 | 0 | #DIV/0!
SM
§Estimated time / actual time
Iteration No. | Estimated time | Actual Time | SM
1 | #REF! | 0.15764 | #REF!
2 | 0 | 0 | #DIV/0!
3 | 0 | 0 | #DIV/0!
4 | 0 | 0 | #DIV/0!
5 | 0 | 0 | #DIV/0!
6 | 0 | 0 | #DIV/0!
7 | 0 | 0 | #DIV/0!
Load factor
Hours/Day | planned and actual per iteration
Iteration No. | Planned Hrs | Actual Hrs
1 | #REF! | 3.1806
2 | #DIV/0! | #DIV/0!
3 | #DIV/0! | #DIV/0!
4 | #DIV/0! | #DIV/0!
5 | #DIV/0! | #DIV/0!
6 | #DIV/0! | #DIV/0!
7 | #DIV/0! | #DIV/0!
Hours per member
| SMK | BB | EL | KJW | #REF! | #REF!
Prog Hrs | 0 | 0 | 0 | 0 | 0 | 0
Non-prog Hrs | 0.15764 | 0.15764 | 0.15764 | 0.15764 | 0 | 0
PPM | Estimated PP hours/actual PP hours (per task)

## Config
Leader
Attended
Programming - Features
Programming - Debugging
Programming - integration
Deployment
Testing - integration (local)
Testing - deployment (cloud)
Testing - Updating Test Log / Test Cases
Team meeting - planning, admin & updates
Team meeting - knowledge sharing
Team meeting - update minutes
Team meeting - other
Project Management - update schedule
Project Management - update metrics
Project Management - other
Design - app architecture (SD etc)
Design - Use Cases
Design - other
Milestone - Preparation
Milestone - Presentations
Other
Yes
No
Not started
Started
Completed
Incomplete
Hold